## Risk Treatment Plan
Risk ID | Risk description | Treatment option | Planned actions | Action owner (illustrative) | Target date (illustrative) | Success criteria | Evidence to collect | Implementation status | Projected residual score | Approval / acceptance | Notes
R-001 | Excessive permissions to patient records | Reduce | MFA; RBAC; least privilege; quarterly access reviews | IT Security Manager | 2026-11-30 | All relevant accounts covered; access reviewed | MFA policy export; access review logs | Proposed | 10 | Pending | Illustrative score; not measured
R-002 | Misconfigured cloud storage | Reduce | Cloud configuration baseline; continuous configuration checks | Cloud Security Lead | 2026-12-15 | No unintended public storage access | Cloud configuration reports; scan results | Proposed | 10 | Pending | Verify actual risk after testing
R-003 | Inadequate recovery safeguards | Reduce | Backup schedule; protected copies; restore testing | IT Operations Lead | 2026-12-15 | Successful documented restore test | Backup logs; restore test report | Proposed | 10 | Pending | Risk may affect availability
R-004 | Insecure API connections | Reduce | Secure API authentication; code review; security tests | Application Security Lead | 2026-12-20 | High-severity findings resolved or formally addressed | API test report; remediation tickets | Proposed | 10 | Pending
R-005 | Insufficient supplier due diligence | Reduce | Supplier risk assessment; security requirements in contracts | Vendor Risk Manager | 2027-01-15 | Critical suppliers reviewed | Vendor questionnaires; contract clauses | Proposed | 8 | Pending
R-006 | Delayed account deprovisioning | Reduce | Automate leaver workflow; periodic account reconciliation | IAM Lead | 2026-12-10 | Leaver access removed within approved SLA | Deprovisioning logs; HR-IAM reconciliation | Proposed | 8 | Pending

## SoA Working Extract
Annex A control | Control name | Applicability | Justification | Implementation status | Evidence to request | Linked risks | Exclusion justification
A.5.15 | Access control | Applicable | Sensitive patient records require controlled access | Proposed | Access control policy; access matrix | R-001
A.5.16 | Identity management | Applicable | Accounts must be managed across identity lifecycle | Proposed | Joiner-mover-leaver procedures; identity inventory | R-001, R-006
A.5.18 | Access rights | Applicable | Permissions require granting, review and removal | Proposed | Access reviews; approval records | R-001, R-006
A.8.5 | Secure authentication | Applicable | Privileged and sensitive access require appropriate authentication | Proposed | MFA policy export; sign-in logs | R-001
A.5.23 | Information security for use of cloud services | Applicable | Cloud storage requires governance and secure use | Proposed | Cloud policy; cloud configuration review | R-002
A.8.9 | Configuration management | Applicable | Cloud settings must be securely configured | Proposed | Configuration baseline; scan results | R-002
A.8.13 | Information backup | Applicable | Availability and restoration of data are essential | Proposed | Backup logs; restore tests | R-003
A.5.30 | ICT readiness for business continuity | Applicable | Healthcare services require recoverability | Proposed | Recovery plans; exercises | R-003
A.8.28 | Secure coding | Applicable | API software needs secure development practices | Proposed | Code review records; secure SDLC guidance | R-004
A.5.19 | Information security in supplier relationships | Applicable | Suppliers can introduce security risk | Proposed | Supplier assessment records | R-005

## Instructions
Purpose | Training-only MediNova risk treatment plan and SoA working extract
Source | Illustrative risks R-001 through R-006 from the MediNova risk register
Important | All entries are fictional; no controls or evidence have been verified
Risk Treatment Plan | Assign accountable owners, deadlines, criteria, evidence, and approvals
SoA extract | Only a selection of Annex A controls; NOT a complete ISO 27001 Statement of Applicability
Complete SoA requires | Assessment of all 93 Annex A controls, inclusion/exclusion justifications, and implementation status
Approval | Actual risk owners must approve risk treatment and any residual risk acceptance
Next step | Validate risk register alignment; replace examples with evidence and authorised decisions