## Risk Register
Risk ID | Asset | Risk scenario | Threat / vulnerability | Likelihood (1-5) | Impact (1-5) | Inherent score | Rating | Treatment | Recommended controls | Risk owner | Status | ISO 27001 control theme
R-001 | Patient records | Staff access to records beyond job needs | Excessive permissions | 4 | 5 | 20 | Critical | Reduce | Least privilege; RBAC; MFA; quarterly access reviews | IT Security Manager | Open | Access control; identity management
R-002 | Cloud storage | Patient documents accidentally exposed publicly | Misconfigured cloud storage | 3 | 5 | 15 | High | Reduce | Private-by-default storage; configuration review; logging | Cloud Operations Lead | Open | Cloud service security; configuration management
R-003 | Clinical portal | Patient service disrupted by ransomware | Phishing and inadequate recovery safeguards | 3 | 5 | 15 | High | Reduce | Backups; restore tests; endpoint protection; phishing awareness | IT Operations Lead | Open | Backup; malware protection; incident management
R-004 | Patient database | Sensitive data lost during transmission | Insecure API connection | 3 | 5 | 15 | High | Reduce | TLS; API authentication; access logging; security testing | Application Security Lead | Open | Cryptography; secure development
R-005 | Third-party OCR provider | Vendor processes sensitive data without adequate safeguards | Insufficient supplier due diligence | 3 | 4 | 12 | High | Reduce | Supplier assessment; contract clauses; data minimisation | Vendor Risk Owner | Open | Supplier relationship security
R-006 | Employee accounts | Former employee retains system access | Delayed account deprovisioning | 4 | 4 | 16 | High | Reduce | Joiner-mover-leaver workflow; access recertification | IAM Lead | Open | Identity management; access rights

## Read Me
MEDINOVA — SIMULATED GRC RISK ASSESSMENT
Purpose | Educational portfolio case study using a fictional healthcare organisation. Not a real audit.
1. Review | Open Risk Register and read each threat, vulnerability and asset.
2. Score | Likelihood and Impact are illustrative assumptions on a 1–5 scale.
3. Calculate | Inherent score = Likelihood × Impact; ratings are Low 1–5, Medium 6–11, High 12–19, Critical 20–25.
4. Treat | Recommended controls are proposals, not verified implementations.
5. Improve | Replace example scores with justified assumptions; add evidence, control owners and residual risk in later lessons.
ISO mapping | Control themes are broad learning prompts, not a formal clause-by-clause ISO/IEC 27001 assessment.
Public sharing | Do not upload patient data, passwords, real company security weaknesses or confidential documents.